## Styled Gantt
Column1 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31
Task | Start Date | End Date | Days | 11/05/2024 | 11/12/2024 | 11/19/2024 | 11/26/2024 | 12/03/2024 | 12/10/2024 | 12/17/2024 | 12/24/2024 | 12/31/2024 | 01/07/2025 | 01/14/2025 | 01/21/2025 | 01/28/2025 | 02/04/2025 | 02/11/2025 | 02/18/2025 | 02/25/2025 | 03/04/2025 | 03/11/2025 | 03/18/2025 | 03/25/2025 | 04/01/2025 | 04/08/2025 | 04/15/2025 | 04/22/2025 | 04/29/2025
|  |  |  | wk 1 | wk 2 | wk 3 | wk 4 | wk 5 | wk 6 | wk 7 | wk 8 | wk 9 | wk 10 | wk 11 | wk 12 | wk 13 | wk 14 | wk 15 | wk 16 | wk 17 | wk 18 | wk 19 | wk 20 | wk 21 | wk 22 | wk 23 | wk 24 | wk 25 | wk 26
Prerequisites of FYP | 2024-11-05 | 2024-11-20 | 15 | bar: wk 1 to wk 3
Research on topics and prepare for Idea Presentation | 2024-11-08 | 2024-11-11 | 3 | bar: wk 1
Start working on proposal of project | 2024-11-12 | 2024-11-20 | 8 | bar: wk 2 to wk 3
Prebuilt documentations | 2024-11-19 | 2024-12-03 | 14 | bar: wk 3 to wk 5
Build the Gantt chart and WBS Diagram | 2024-11-21 | 2024-11-23 | 2 | bar: wk 3
Work on architecture diagram | 2024-11-24 | 2024-11-27 | 3 | bar: wk 3 to wk 4
Deliver Figma design and Literature review | 2024-11-25 | 2024-12-03 | 8 | bar: wk 3 to wk 5
User Management | 2024-12-03 | 2025-01-01 | 29 | bar: wk 5 to wk 9
Complete the prototype and literature review report | 2024-12-04 | 2024-12-09 | 5 | bar: wk 5
Work for user registration frontend | 2024-12-16 | 2024-12-21 | 5 | bar: wk 6 to wk 7
Build database design diagram | 2024-12-10 | 2024-12-15 | 5 | bar: wk 6
Integrate the backend section and also develop the login functionality | 2024-12-22 | 2024-12-28 | 6 | bar: wk 7 to wk 8
Use email verification and JWT token for better authorization | 2024-12-28 | 2025-01-01 | 4 | bar: wk 8 to wk 9
Exercise Library | 2025-01-04 | 2025-02-10 | 37 | bar: wk 9 to wk 14
Reasearch for the database and other applications for references | 2025-01-04 | 2025-01-08 | 4 | bar: wk 9 to wk 10
Handle the api call and create front end views for the exercise part | 2025-01-09 | 2025-01-23 | 14 | bar: wk 10 to wk 12
Integrate the backend models to store the data of users. | 2025-01-24 | 2025-02-06 | 13 | bar: wk 12 to wk 14
Make user able to add and delete libraries and same with the exercies under it | 2025-02-01 | 2025-02-08 | 7 | bar: wk 13 to wk 14
Study of the mechanism of calculating calories burn | 2025-02-06 | 2025-02-10 | 4 | bar: wk 14
Nutrition/ Diet | 2025-02-11 | 2025-03-04 | 21 | bar: wk 15 to wk 18
Search for nutrition database with dietry preference | 2025-02-11 | 2025-02-15 | 4 | bar: wk 15
Insert the user dietry plans inside our database | 2025-02-26 | 2025-03-04 | 6 | bar: wk 17 to wk 18
Integrate the api and enhance user experience | 2025-02-16 | 2025-02-25 | 9 | bar: wk 15 to wk 17
Pose Estimation | 2025-03-05 | 2025-04-09 | 35 | bar: wk 18 to wk 23
Integrate the frontend sections for pose estimation part | 2025-03-05 | 2025-03-11 | 6 | bar: wk 18 to wk 19
Search for the api and package for working with pose estimation for your frontend | 2025-03-12 | 2025-03-25 | 13 | bar: wk 19 to wk 21
Build the logic for calculating angles and work on more precise angle measurement | 2025-03-26 | 2025-04-02 | 7 | bar: wk 21 to wk 22
Add backend to add history of the pose estimation and pose for user | 2025-04-03 | 2025-04-09 | 6 | bar: wk 22 to wk 23
Setting and Dashboards | 2025-04-10 | 2025-05-02 | 22 | bar: wk 23 to wk 26
Add the graph based user Performance tracking for exercise and meals | 2025-04-25 | 2025-05-02 | 7 | bar: wk 25 to wk 26
Graph section for calorie burned from food and exercises. | 2025-04-20 | 2025-04-24 | 4 | bar: wk 24 to wk 25
Manage the user profile credential update | 2025-04-10 | 2025-04-14 | 4 | bar: wk 23
Add calendar functionalities to track the streak for exercise performed | 2025-04-15 | 2025-04-19 | 4 | bar: wk 24
QA